## Evaluation_report
Section | Activity / Indicator | Responsible Person(s) | Planned Timeline | Completion Status (Yes/No) | Quality Rating (1-5) | Issues / Risks Identified | Corrective Action | Comments
PURPOSE
Purpose | Safety of equipment and documents ensured | Martin, Ben | Move Day
Purpose | Move completed cost-effectively | Martin, Ben | Move Day
SCOPE
Scope | Office furniture relocated (chairs, tables, reception desk) | Relocation Team | Move Day |  |  |  |  | done
Scope | Office equipment relocated (files, whiteboards, printer) | Relocation Team | Move Day |  |  |  |  | done
Scope | Appliances relocated (water dispenser, fridge, microwave) | Relocation Team | Move Day |  |  |  |  | done
Scope | WiFi disconnected from old premises | Ben | Move Day |  |  |  |  | Not Yet
Scope | WiFi installed at new premises | Ben, Savannah | Post-Move (Sat/Sun) |  |  |  |  | Not Yet
Scope | Signage removed and relocated | Martin, Ben | Move Day |  |  |  |  | Not Yet
PRE-RELOCATION PLANNING
Planning | Lease/ownership documents confirmed | Martin | Week 1 |  |  |  |  | Not Yet
Planning | Power supply and sockets inspected | Martin, Ben | Week 1 |  |  |  |  | Not Yet
Planning | Internet connectivity verified | Martin, Ben | Week 1 |  |  |  |  | Not Yet
Planning | Water and sanitation checked | Martin, Ben | Week 1 |  |  |  |  | done
Planning | Security assessed (locks, doors, windows) | Martin, Ben | Week 1 |  |  |  |  | done
Planning | Ventilation and lighting verified | Martin, Ben | Week 1 |  |  |  |  | Not Yet
Planning | Office spaces allocated | Ben, Martin, Daphne | Week 1 |  |  |  |  | Not Yet
Planning | Storage areas designated | Ben, Martin, Daphne | Week 1 |  |  |  |  | Not Yet
Planning | Reception and common areas planned | Ben, Martin, Daphne | Week 1 |  |  |  |  | Not Yet
ASSETS & INVENTORY
Assets | Detailed inventory created | Ben | Week 1 |  |  |  |  | done
Assets | Items tagged (Move/Dispose/Donate/Store) | Ben | Week 1 |  |  |  |  | done
Assets | Fragile items identified | Martin, Ben | Week 1 |  |  |  |  | done
Assets | Sensitive items identified | Martin, Ben | Week 1 |  |  |  |  | done
Assets | High-value items identified | Martin, Ben | Week 1 |  |  |  |  | done
Assets | Fragile & sensitive items secured during move | Martin, Ben | Move Day |  |  |  |  | done
COMMUNICATION
Communication | Staff notified of relocation date | Martin | 2 weeks before | Yes |  |  |  | Done
Communication | Staff expectations communicated | Ben | 2 weeks before |  |  |  |  | Done
Communication | Stakeholders informed (clients, suppliers) | Martin | 2 weeks before |  |  |  |  | Done
Communication | Internal documents updated | Martin, Ben | Week 2 |  |  |  |  | Not Yet
Communication | Emergency contacts updated | Martin, Ben | Week 2 |  |  |  |  | Not Yet
LOGISTICS & TRANSPORTATION | [7 empty] | Not Yet
Logistics | Pickup truck(s) hired | Martin, Ben | Move Day |  |  |  |  | Negotiations done
Logistics | Number of trips determined | Martin, Ben | 1 week before |  |  |  |  | Max 2
Logistics | Loading team arranged | Ben | Move Day |  |  |  |  | done
Logistics | Offloading team arranged | Ben | Move Day |  |  |  |  | Done
Logistics | Boxes labeled by department/room | Ben | 3 days before |  |  |  |  | Done
Logistics | Boxes color-coded | Ben | 3 days before |  |  |  |  | Done
Logistics | Confidential documents separated | Martin, Ben | 3 days before |  |  |  |  | Done
Logistics | Fragile items packed separately | Martin, Ben | 3 days before |  |  |  |  | Done
MOVE DAY EXECUTION
Move Day | Transport arranged and on time | Ben | Move Day |  |  |  |  | done
Move Day | Loading completed safely | Loading Team | Move Day |  |  |  |  | done
Move Day | All items transported successfully | Relocation Team | Move Day |  |  |  |  | done
Move Day | Offloading completed safely | Offloading Team | Move Day |  |  |  |  | done
Move Day | No items damaged during transport | Relocation Team | Move Day |  |  |  |  | done
Move Day | No items lost during transport | Relocation Team | Move Day |  |  |  |  | confirmed
POST-MOVE SETUP
Post-Move | New premises inspected for cleanliness | Ben, Martin | Before Move |  |  |  |  | Done and Ongoing
Post-Move | Cleaning cost negotiated | Ben, Martin | Before Move |  |  |  |  | done by Stepen
Post-Move | Premises cleaned and ready | Ben, Martin | Post-Move |  |  |  |  | Not Yet
Post-Move | Internet connectivity installed | Ben, Savannah | Sat/Sun |  |  |  |  | Not Yet
Post-Move | Internet tested and working | Ben, Savannah | Sat/Sun |  |  |  |  | Not Yet
Post-Move | Printers installed | Ben | Sat/Sun |  |  |  |  | Not Yet
Post-Move | Scanners installed | Ben | Sat/Sun |  |  |  |  | Not Yet
Post-Move | All equipment tested | Ben | Sunday |  |  |  |  | Not Yet
OPERATIONAL STABILIZATION
Stabilization | Outstanding setup issues identified | Martin, Ben | Sunday |  |  |  |  | Not Yet
Stabilization | Outstanding issues resolved | Martin, Ben | Before Monday |  |  |  |  | Not Yet
Stabilization | Staff orientation conducted | Martin, Ben | Monday 7:30-8am |  |  |  |  | Not Yet
Stabilization | Operations resumed normally | All Staff | Monday 8am |  |  |  |  | Not Yet
OLD PREMISES HANDOVER
Handover | All remaining items removed | Relocation Team | After Move |  |  |  |  | done
Handover | Old premises cleaned | Relocation Team | After Move |  |  |  |  | Not Yet
Handover | Damages repaired | Martin, Ben | After Move |  |  |  |  | Not Yet
Handover | Keys returned | Martin | Final Day |  |  |  |  | done
Handover | Handover documents signed | Martin | Final Day |  |  |  |  | done
REVIEW & DOCUMENTATION
Review | Post-move review meeting conducted | Martin, Ben, Management | Week After |  |  |  |  | Not Yet
Review | Lessons learned documented | Martin, Ben | Week After |  |  |  |  | Not Yet
Review | Asset registers updated | Ben, Martin | Week After |  |  |  |  | Not Yet
Review | Location records updated | Ben, Martin | Week After |  |  |  |  | Not Yet

## Budget_Tracking
No. | Category | Item | Estimated Cost (UGX) | Actual Cost (UGX) | Variance (UGX) | Payment Status | Receipt/Invoice No. | Comments
1 | Transport | Truck hire | 120000 | 120000 |  |  |  | negotiated
2 | Labor | Loading team | Covered in Truck hire |  |  |  |  | covered
3 | Labor | Offloading team | Covered in Truck hire |  |  |  |  | covered
4 | Materials | Boxes and labels | [5 empty] | covered
5 | Materials | Packing materials | [5 empty] | covered
6 | IT Setup | Internet installation | [5 empty] | not yet
7 | IT Setup | Network equipment | [5 empty] | not yet
8 | Cleaning | New premises cleaning | [5 empty] | started
9 | Cleaning | Old premises cleaning | [5 empty] | not yet
10 | Repairs | New premises repairs | [5 empty] | ongoing
11 | Repairs | Old premises repairs | [5 empty] | not yet
12 | Signage | Signage relocation | [5 empty] | not yet
13 | Contingency | Unforeseen expenses (10-15%) |  | 20000 |  |  | facility cleaning | covered and to be refunded
| TOTAL |  |  | 140000

## Inventroy_Tracking
Item No. | Item Description | Quantity | Condition (Good/Fair/Poor) | Action (Move/Dispose/Store) | Priority (Regular/Fragile/Confidential) | Packed (Yes/No) | Loaded (Yes/No) | Delivered (Yes/No) | Location in New Premises | Comments
1 | Office chairs/platic | 13 |  | Move | Regular | No | No | No |  | Undone
2 | Plastic tables | 5 | Good | Move | Regular | No | No | No |  | Undone
3 | Reception table | 1 | Good | Move | Regular | No | No | No |  | Undone
4 | Filing cabinets | 0 |  | Move | Regular | No | No | No |  | Undone
5 | Document files | 30 | Good | Move | Confidential | No | No | No |  | Undone
6 | Whiteboards | 9 | Good | Move | Fragile | No | No | No |  | Undone
7 | Printer | 1 | Good | Move | Fragile | No | No | No |  | Undone
8 | Water dispenser | 1 | Good | Move | Regular | No | No | No |  | Undone
9 | Refrigerator | 1 | Good | Move | Regular | No | No | No |  | Undone
10 | Microwave | 1 | Good | Move | Regular | No | No | No |  | Undone
11 | Utensils/cups/plates/containers | 32 piecies | Good | Move | Regular | No | No | No |  | Undone
12 | Student Chairs | 21 | Good | Move | Regular | No | No | No |  | Undone

## Summary_Dashboard
Metric | Value | Target | % Complete
Total Activities | 60 | 60 | 0%
Completed Activities | 1 | 60 | 2%
Pending Activities | 59 | - | -
Average Quality Rating
Budget Spent
High Priority Issues
Days to Move | 2 | 2 | 0%
QUALITY RATING SCALE
5 = Excellent (Exceeded expectations, no issues)
4 = Good (Met expectations, minor issues resolved)
3 = Satisfactory (Met basic requirements, some issues)
2 = Poor (Below expectations, significant issues)
1 = Unsatisfactory (Failed to meet requirements)